## Bug Tracker
ID | Module | Feature | Reported By | Assigned To | Description of Bug | Severity | Priority | Status | Date Reported | Target Fix Date | Remarks / Screenshot Link
1 | Admin | Login Captcha | Shanthini | Sanjit | Please change the captcha pattern difficult to enter | High | P1 | Open | 2025-11-15 |  | Feels difficult to find the captcha letters which encounter more than 2 3 captcha
2 | Admin | Chatbot | Shanthini | Sanjit | Chatbot is taking too much time to respond and occasionally shows an error | Medium | P2 | Open | 2025-11-15
3 | Admin | Appointment of new patient | Shanthini | Sanjit | New patient appointment not able save | High | P1 | Open | 2025-11-15
4 | Admin | Payroll Management | Shanthini | Sanjit | Not able to view the employee the Payroll | High | P1 | Open | 2025-11-15 |  | Not able to view employee payroll.
5 | Admin | Payroll Management | Shanthini | Sanjit | Not able to edit the employee the Payroll | Critical | P1 | Open | 2025-11-15
6 | Admin | Payroll Management | Shanthini | Sanjit | Taking too much loading time | Medium | P2 | Open | 2025-11-15
7 | Admin | Pathology | Shanthini | Sanjit | Not able to view the patient details | High | P1 | Open | 2025-11-15
8 | Admin | Pathology | Shanthini | Sanjit | Not able to edit the patient details | Critical | P1 | Open | 2025-11-15
9 | Admin | Pathology | Shanthini | Sanjit | Taking too much loading time | Medium | P2 | Open | 2025-11-15
10 | Admin | Pharmacy | Shanthini | Sanjit | Stocks are coming "0" by default | High | P1 | Open | 2025-11-15
11 | Doctor | Dashboard | Shanthini | Sanjit | Patient queue is empty , though we have 1 patient | Medium | P2 | Open | 2025-11-15
12 | Doctor | Appointment of new patient | Shanthini | Sanjit | The reason and status fields are not displaying clearly. Also, there is no clear section for the doctor to enter the medication details. | High | P1 | Open | 2025-11-15
13 | Pharmacy | Dashboard | Shanthini | Sanjit | The prescription dashboard is showing 0 for all values. I think this is because no sample prescriptions have been added. Please add a few sample prescriptions so the dashboard and functions (edit/delete/update) can be tested. | High | P1 | Open | 2025-11-15
14 | Pharmacy | Medicine inventory | Shanthini | Sanjit | Medicine Inventory shows error | Critical | P1 | Open | 2025-11-15
15 | Pathology | Add report | Shanthini | Sanjit | Getting 404 error | High | P1 | Open | 2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15
2025-11-15

## Dashboard
Metric | Value
Total Bugs | 4
Open Bugs | 1
In Progress | 1
Fixed | 1
Closed | 1